Draft WP5.3 | Detailed Workplan
Mokhtar Sellami (MESRS), co-task leader
Version 01 | 28 Feb. 2021

### Task 5.3: Strategy for RE research-capacity in Africa
Start date: M3 (Dec. 2020); End date: M63 (Dec. 2025)
Task Leaders:
- Mr Mokthar Sellami & Mr Belarbi Yacine & Ms Souami Feriel | MINISTERE DE L'ENSEIGNEMENT SUPERIEUR ET DE LA RECHERCHE SCIENTIFIQUE (MESRS)
- Ms Elke Dall & Mr Dietmar Lampert & Mr Utku Demir | Zentrum für Soziale Innovation (ZSI)
Contributors:
- Mr Abdellatif Zerga & Mr Erick Tambo | Pan African University Water and Energy Science (PAUWES)
- Mr Stefan A. Haffner | German Aerospace Center (DLR)
- Ms Tinyiko Ntshongwana & Ms Refilwe Mashigo |Department of Science and Innovation (DSI)
- Mr Izael da Silva & Ms Anne W. Wambugu | Strathmore University (SU)

T5.3	PM formerly	PM modification	Final PM	Comments
MESRS (lead)	3	2	5
ZSI (lead)	2	0	2
PAUWES	2	-2	0
DLR	2	-2	0
DSI	0	2	2
SU	0	2	2
UNU	2	0	0
			11	Total - T5.3

This task addresses innovative models of cooperation for R&I capacity-building. African strategic agendas will be analysed and selected activities in the field of RE will be benchmarked. The target is to support new (or existing) mechanisms which may involve networking, teaming (by creating centres of excellence), twinning (institutional co supervision, post-doctoral programmes), and sharing infrastructures. The framework of such vision was declined in the new Africa-Europe Alliance for Sustainable Investment and Jobs, Horizon Europe and the new Research Framework Programme for the period 2021-2027 that open up new opportunities in the join AU-EU strategy (5th SOM, AU-EU HLPD on STI). This work will be undertaken Toward innovative models of cooperation for R&I capacity-building in RE following the five next steps:

 (1) Analysing African strategic agendas in RE [SDGs, Africa2063, STISA] and Selecting activities in the field of RE [Areas or research and innovation, research programs, keywords]
(2) Benchmarking AU-EU R&I in RE [by domain and by African regions based on bilateral scientific cooperation, identified keywords]
(3) Mapping and visualising results of networks [nodes are countries, institutions]
(4) Identifying R&I partnership [Institutions, training programmes, pooling or access to Infrastructures].
(5) Strengthening existing mechanisms or launching new mechanisms for networking
- teaming (by creating centres of excellence),
- twinning (institutional co-supervision, post-doctoral programmes),
- sharing infrastructures.
the new Africa-Europe Alliance for Sustainable Investment and Jobs, Horizon Europe and the new Research Framework Programme for the period 2021-2027 that open up new opportunities in the join AU-EU strategy (5th SOM, AU-EU HLPD on STI).

(1) Analysing African strategic agendas in RE [SDGs, Africa2063, STISA] and selecting activities in the field of RE [Areas or research and innovation, research programs, keywords]

1.1] SDGs and African Agenda Analysis (M1 to M6): Comparison of the SDG Agenda 2030, the Agenda 2063 « Africa we want », including STISA (2014-2024) objectives in RE-related capacity
Goal 7 of the SDGs aims at achieving universal access to affordable, reliable, sustainable and modern energy by 2030, while Agenda 2063 (including STISA objectives) has targets for an increase of 50% in electricity generation, 50% distribution and 70% of Africans having access to electricity by 2023. But the growth of Africa’s sustainable development is underpinned by a set of target categories connected to Renewable Energy, with strong level of relevance.
- SDG1: Poverty and Development
- SDG3: Disease and Mortality
- SDG4: Ensure inclusive and equitable quality education and promote lifelong learning opportunities for all
- SDG5: Achieve gender equality and empower all women and girls
- SDG6: Ensure access to water and sanitation for all
- SDG7: Ensure access to affordable, reliable, sustainable and modern energy
- SDG9: Inclusive and Sustainable Industrialization
- SDG11: Make cities inclusive, safe, resilient and sustainable
- SDG12: Ensure sustainable consumption and production patterns
- SDG13: Take urgent action to combat climate and its impacts

1.2] Selecting activities in the field of RE [Areas or research and innovation, research programs, initiatives, keywords]
For each Agenda2030 SDGs AND/OR Africa2063 target an excel file is under construction including the following information’s:
1. Targets linked to renewable energy and its relevance [strong, high, weak]
2. Associated keywords or string
3. Which RE technologies could solve [1. Solar Photovoltaic Energy, 2. Wind Energy, 3. Energy Efficiency in the Building, 4. Solar Thermal Energy, 5. Marine energy, 6. Storage of Energy, 7. Geothermal Energy, 8. Bioenergy, 9. Hydrogen and Fuel Cells, 10. Hydroelectricity, 11. Materials : (industrialization of certain components of renewable energy systems such as solar panels or wind turbine blades)].
4. Current African initiatives and Feedback of visible implemented programs or actions, based on reports on STISA or Africa2063 Evaluation process
(2) Benchmarking (M1 to M12): The benchmarking process is used to identify and analyze previous projects to determine their impact on the local or regional community, and to identify the human capacity as potential resource for R&I.
2.1) Benchmarking the LEAP-RE projects in Pillar 2 and the coming projects in Pillar1.
To identify how LEAP-RE projects could be connected to AU-EU R&I needs, we’ll first use a matching process and comparison between the objectives of the six multi-annual roadmaps, thanks to the associated keywords, the technical keywords identified in the matrix of step [1] and the selected programs in Pillar2. This action will be completed next December 2021 based on the projects which will be accepted and funded under Pillar1.
Multiannual roadmaps	PillarII projects	Keywords	Connexion to matrix (step1)
Example with Multiannual roadmap 6….
6: Innovative solutions for priority domestic uses (clean cooking and cold chain)	WP10 PURAMS, solar cooking, standalone solar cooker, silicon solar cells,	clean cooking; energy poverty; improved cooking stoves; Electric clean cooking, Improved cookstove, Solar cooker, Cold chain, Supply chain, Cold chain logistics	saves health, time and money [SDG1], job opportunities [SDG8], Reducing smoke emissions, air pollution [SDG3], climate vulnerability [SDG11], girls kept out of school [4], etc…

2.2) Benchmarking (M1 to M12): AU-EU past projects (e.g. FP7-ERAfrica, MED-Spring, AU Grant projects and H2020 projects in sustainable energy).
The characteristic of the R&I partnership is to strive to integrate research and innovation activities that have an impact on citizens. Thus, it will be assisted by the valuable lessons learned from projects developed or underway in the field of sustainable energy; these are AU grant projects in renewable and sustainable energies, or EU projects. We can mention, but not limited to AREI (Africa Renewable Energy Initiative (AREI), CSP4Africa (Development of a cost-effective, modular and dry concentrating solar power for Africa), REELCOOP (REnewable ELectricity COOPeration), SOLPART(High temperature Solar-Heated Reactors for Industrials Production of Reactive Particulates), ECOWAS observatory for renewable energy and energy efficiency, EUROSUNMED  “Euro-Mediterranean Cooperation on Research & Training in Sun based Renewable Energies.. ”, etc. This overview of two binary digit research programs offers particularly to identify the gaps of research and cooperation activities, which is an issue of high priority to the EU-AU R&I Partnership in RE.

 3) Mapping and visualising results of networks in RE (nodes are countries and/or institutions)
3.1) Visualising LEAP-RE network partners (Institutions involved in Pillar1, Pillar2, Pillar3). This exercise is just to illustrate graphically the link between research teams and institutions for mobility or access to the infrastructures. Nodes providing services as sharing infrastructures will be highlighted with indication of the scientific equipment.
3.2) Scientometric analysis of high ranked publications of African researchers and their partners in renewable energy using Clarivate’s Web of Science data bases
Facing RE priorities requires analyses based on credible data and the involvement of institutional leaders in the public- and private sectors, along with a mobilization of the RE community. Within this framework we’ll work to establish a mapping of the knowledge sharing and transfer to sustain the innovation process in African countries.
This mapping will cover the identification of scientific networks and publications, as well as universities, faculties and research teams. In addition, investigating existing cooperation and the mobility of students and researchers will facilitate the elaboration of the road-map in areas of common interest for medium and long-term-milestones and the strengthening of capacities to build a broader engagement between African and European Research and Innovation communities.
It is important to identify scientific researchers in Africa, by country and by region, not only in RE, but the mapping will be extended to sub or connected areas as reported in the matrix (ref SDG4, … , SDG9, SDG11).
For the identification of regions, we shall adopt the United Nations geoscheme for Africa: North Africa, West Africa, East Africa, Central Africa and Southern Africa. For each country we’ll give a general overview of top 15 institutions, top 15 countries of co-publishing and top 15 leading scientists. We’ll summarize these results in some graphics to show the regional and continental map of scientific capacities and the importance of the links between these communities.
Our instrument of work is the web of science (WOS), a search and discovery platform for more than 7,000 academic and research institutions. It is a product of “Thomson Reuters Institute of Scientific Information” (ISI) and includes above 12,000 high impact journals and 16.000 conference proceedings, reports, and book series. Publications in WoS are classified in 254 categories or 152 Research Areas. Additional useful metrics are sources/journals, authors, affiliation institutions, affiliation countries, citations, funding agencies, organizations, editors. It is important to highlight that in our search we’ll focus only on European, African, and international institutions .
Embedded analysis tools help to refine results, identify top authors, institutions, and publishers in a given field, trace citations, facilitate discoveries and connections across disciplines, regions and institutions. The methodology will be explained first then the limits of such work. The output will be first a general map showing the potentiality in research for each African country/region.
This work will be conducted for each multiannual roadmap in RE with recommendations and/or indicators on building and/or upgrading research infrastructures, enhancing professional and technical competencies based on the national policy if such strategy exists. Collaborative effort between researchers from both continents will be proposed as an option for developing the needed knowledge capacities for maintaining and strengthening long term collaborations by teaming and twinning actions.
Examples of search queries about MAR 6 for North African region. This search query is to execute for each pillar AND for each African region + specific top 10 countries depending on the number of records and publications.
([TS = (cocking or ”clean cooking” or “cooking stoves” or “Electric clean cooking” or “Solar cooker”)])	AND CU= (Algeria or Egypt or Libya or Morocco or Tunisia or Mauritania)	OUTPUTS: / - Graph mapping will be established by adopting the approach of visualization of similarities using optimized algorithms from VOSviewer 1.6.5 and Gephi Sotware, etc.. / - ranking and analyse by country, funding agencies, affiliation institutions, authors / - identification of research teams on specific thematics in RE and their position (ranking) in Africa
([TS = (“Cold chain” or “Supply chain” or “Cold chain logistics”)])	AND CU= (Algeria or Egypt or Libya or Morocco or Tunisia or Mauritania)

(4) Identifying R&I partnership [Institutions, training programmes, pooling or access to Infrastructures].
4.1) Analyzing identified nodes of the network and moving to a long-lasting partnership: Strengthening and maintaining research capacities are the fundamental pillars to generate knowledge, facilitate learning and co-develop innovations in sustainable energy. A comprehensive approach is needed to build research capacity and institutional strengths particularly in Africa. We have identified a set of mechanisms (twinning, teaming and pooling) to launch after undertaking an audit where such research infrastructure collaboration will be most profitable. The first step will be to prepare a questionnaire to identify which actions are possible, when, with which means (not necessarily funding) and with who.
- Preparation of a swot / questionnaire / round tables with identified and selected partners in both continents.
These actions will be explored with selected and willing institutions engaged for the future Europe-Africa cooperation. They are to develop.

 (5) Strengthening existing mechanisms or launching new mechanisms for networking
- teaming (by creating centres of excellence),
- twinning (institutional co-supervision, post-doctoral programmes),
- sharing infrastructures.
- Revitalizing of universities

• Twinning, teaming and pooling (M6 to M60): Deliver virtual networks of academic communities in RE, with mechanisms for linking scientists and institutions that are committed to working together based on these three collaboration instruments:
– Twinning in post-doctoral programmes: institutions of the network receive researchers selected to conduct a specific task
– Teaming supports the creation of new (or upgrading of existing) Centres of Excellence in partner countries. This mechanism is inspired from Horizon 2020 “Teaming for Excellence” programme to transfer experience from Europe’s top research centres to the new EU MS.
– Pooling of resources provides access to world-class infrastructures to do cutting-edge research in partnership with European institutions depending on their internal legislation.
- Revitalizing of universities and other training institutions in RE;