## Slide 1: LEAP-RE Kick-OFF MEETING 23-24 March 2021
Work Package 5
Long-term Perspective

## Slide 2: Long-term Perspective
5

## Slide 3: WP 5: Introduction
Duration: M3 (Dec. 2020) – M63 (Dec. 2025)
21 Partners involved:

## Slide 4: WP 5: Introduction
Main WP objectives:
Developing the long-term perspective for the AU-EU partnership in RE STI
Monitoring, Evaluation & Learning (MEL) Concept
MEL process with Pillar 1, Pillar 2 and Pillar 3 activities
Dialogues with policymakers and other stakeholders for research uptake
A Strategies for RE research-capacity in Africa
Strategy guidelines and plan for the design of the long-term partnership

## Slide 5: WP 5: Milestones and outcomes
Main WP expected results:
  Baseline study | Theoretical framework development | MEL Plan | Monitoring | Evaluation | Learning
  Analysis about R&I capacities in Africa
  Twinning & Teaming & Pooling activities
  List of new LEAP-RE community members
  Strategy guidelines and a plan for the design of the long-term partnership
Main WP milestones:
  M55: Launch of the future partnership in M58 (Jul. 2025)

## Slide 6: WP 5: Task 5.1
Task 5.1: M&E Concept and Impact Assessment
Leaders and contributing partners: Ms Elena SIMION (UEFISCDI) | Ms Anne W. Wambugu & Ms Hope N Njoroge (SU) | Mr Stefan A. Haffner (DLR) | Mr Abdellatif Zerga & Mr Erick Tambo (PAUWES) | Mr Mokthar Sellami & Mr Belarbi Yacine & Ms Souami Feriel (MESRS) | Ms Elke Dall & Mr Dietmar Lampert & Mr Utku Demir (ZSI)
Duration: (M3 (Dec. 2020) - M63 (Dec. 2025))
Main Activities: Monitoring, Evaluation and Learning
Methodology : Baseline study | Theoretical framework development | MEL Plan | Monitoring | Evaluation | Learning
Expected results: MEL Plan and MEL Reports for all three Pillars of the project
Deliverables:
Year | Number | Title | Due Date | Responsible
2021 | D5.1 | Theory of Change, M&E Approach and MEL Plan | M9 ¦ Jun. 2021 | SU – Anne W. Wambugu
2025 | D5.2 | Report on Monitoring | M53 ¦ Feb. 2025 | SU - Anne W. Wambugu
 | D5.3 | Report on Evaluation and Learning | M61 ¦ Oct. 2025 | UEFISCDI - Elena SIMION

## Slide 7: WP 5: Task 5.2
Task 5.2: Dialogue with Policymakers and other Stakeholders for Research Uptake
Leaders and contributing partners: Mr Abdellatif Zerga & Mr Erick Tambo (PAUWES) | Mr Stefan A. Haffner (DLR) | Mr Mokthar Sellami & Mr Belarbi Yacine & Ms Souami Feriel (MESRS) | Ms Emanuela Colombo & Mr Riccardo Mereu (POLIMI) | Ms Niclette Bukasa Kampata (LGI)
Duration: (M3 (Dec. 2020) - M63 (Dec. 2025))
Main Activities: Institutional dialogues with policy makers and other stakeholders
Methodology: (Virtual) Round table discussions:
  1) “Theory of Change and Impact Pathway in Multi-lateral Cooperations?”
  2) “Monitoring, Evaluation and Learning in an AU-EU Knowledge Management and Communication Framework”,
  3) “Coordinated Communication in the Stakeholder’s Network Labyrinth”
  4) “AU-EU Knowledge Hubs System”
Expected results: Contributions to the ‘Strategy guidelines and plan for the design of the long-term partnership’
Deliverables:
Year | Number | Title | Due Date | Responsible
2024 | D5.5 | Research briefs based on Pillar 1 and Pillar 2 results for dialogue with external policy and stakeholder partner | M40 ¦ Jan. 2024 | PAUWES – Erick Tambo
 | D5.4 | Proceedings of round tables for research uptake | M43 ¦ Apr. 2024 | PAUWES – Erick Tambo

## Slide 8: WP 5: Task 5.3
Task 5.3: Strategy for RE research-capacity in Africa
Leaders and contributing partners: Mr Mokthar Sellami & Mr Belarbi Yacine & Ms Souami Feriel (MESRS) | Ms Elke Dall & Mr Dietmar Lampert & Mr Utku Demir (ZSI) | Ms Tinyiko Ntshongwana & Ms Refilwe Mashigo (DSI) | Ms Anne W. Wambugu& Ms Hope N Njoroge | Strathmore University (SU)
Duration: (M3 (Dec. 2020) - M63 (Dec. 2025))
Main activities: Analysis, mapping & visualization of networks, evaluation & Strengthening EU-AU R&I capacities
Methodology / suggested approach:
  Benchmarking, bibliometric analysis, questionnaire prep.
  Strengthening EU-AU R&I capacities
Task expected results: Report on RE-related R&I capacities, excellence centres in Africa as well as research co-operation and institutional networks with other regions & Building AU-EU R&I Networks
Deliverables:
Year | Number | Title | Due Date | Responsible
2021 | D5.8 | Report on the analysis about R&I capacities in Africa | M15 ¦ Dec. 2021 | MESRS – Mokthar Sellami
2025 | D5.9 | Report about Twinning & Teaming & Pooling activities | M58 ¦ Jul. 2025 | MESRS – Mokthar Sellami

## Slide 9: WP 5: Task 5.4
Task 5.4: Strategic ambition of the long-term partnership
Leaders and contributing partners: Mr Abdellatif Zerga & Mr Erick Tambo (PAUWES) | Mr Stefan A. Haffner (DLR) | Ms Elena SIMION (UEFISCDI) | Ms Anne W. Wambugu & Ms Hope N Njoroge (SU) | Ms Kibibi Ndope (AESG) | Ms Melissa Plath | HELSINGIN YLIOPISTO (HU)
Duration: (M3 (Dec. 2020) - M63 (Dec. 2025))
Main activities: Analysis, document writing, (virtual) round tables & internal (virtual) workshop(s)
Methodology: Collating lessons learned from external actors.
Expected results: Strategy guidelines and a plan for the design of the long-term partnership & List of new LEAP-RE community members
Deliverables:
Year | Number | Title | Due Date | Responsible
2024 | D5.11 | Strategy design workshop for the future platform and documentation of lessons learned from external actors | M50 ¦ Nov. 2024 | DLR - Stefan A. Haffner
2025 | D5.6 | Funding opportunities to enhance additional activities | M53 ¦ Feb. 2025 | PAUWES – Erick Tambo
 | D5.7 | List of new LEAP-RE community members | M53 ¦ Feb. 2025 | DLR - Stefan A. Haffner
 | D5.10 | Strategy guidelines and plan for the design of the long-term partnership | M53 ¦ Feb. 2025 | DLR - Stefan A. Haffner

## Slide 10: WP 5: Interactions with other WP
Input from other WPs:
T5.1: WP1, WP2, WP3, WP4 in the field of MEL (plan and activities) as well as for the design of a long-term MEL mechanism.
T5.2: Information from WP4 about their short & mid-term activities and network actors towards the design of long-term knowledge management and communication mechanism, principles and network of actors. MEL related input from other WPs will be channelled through T5.1.
T5.3: Closest Interaction with WP4 and African European research institutions
T5.4: Information from other WPs about the basic needs in the Platform regarding knowledge management and communication as well as about the MEL approach will be channeled through T5.1 and T5.2
Output for other WP:
T5.1: WP1, WP2, WP3, WP4 in the field of MEL for the MEL plan and activities as well as for the design of a long-term MEL mechanism
T5.2: Contacts to new network actors, information about basic needs expressed in round tables
T5.3: Identified projects and teams to consolidate AU-EU partnership
T5.4: Meta-governance and coordination model to feed WP6 process towards the AU-EU Platform on RE

## Slide 11: WP 5: Actions done in the first months
T5.1: None, except contributions to the Detailed WorkPlan (DWP)
T5.2: None, except contributions to the Detailed WorkPlan (DWP)
T5.3:
  Keyword identification for the bibliometric analysis, query comparison to measure the validity of the expected input data.
  Benchmarking AU-EU R&I in RE, Scientometric analysis of high ranked publications of African researchers in RE, Mapping and visualising results of networks
T5.4: None, except contributions to the Detailed WorkPlan (DWP)

## Slide 12: WP 5: Actions to be done
Actions list to be launch/implement in the first 6 months
T5.1: MEL Plan/ Sep. 2021 | Anne W. Wambugu SU
T5.2: Draft concepts of 4 round tables | Apr. 2021 | Erick Tambo (PAUWES) & Stefan A. Haffner (DLR)
T5.3:
  (i) Bechmarking / Sep. 2021 (ii) Bibliometric Research / Mar. 2021 / ZSI-Team (Elke Dall, Dietmar Lampert, Utku Demir)
  Mapping of AU-EU R&I capacities / Mar. 2022 / Mokhtar Sellami (MESRS) Elke Dall (ZSI)
T5.4: Draft D5.10 ‚Strategy guidelines and plan for the design of the long-term partnership’ | Jul. 2021 | Erick Tambo (PAUWES) & Stefan A. Haffner (DLR)

## Slide 13: WP 5: Risk assessment
Risk assessment and Contingency plan
Describe any risk associated to the implementation of the work to be carried out / add a contingency action / feel free to use a table
Risk Name | Impact if occurs | Preventive / Contingency action
Involvements of European research institutions in participating to train African capacities | Moderate | Sensibilization, rely on the partner institutions of the project
Lack of response and attention in the AU-EU HLPD and relevant ministries of the member states to the WP5 process and its results | High | Constant contact with the HLPD Bureau and the ministries / project management agencies involved in LEAP-RE