## Slide 1: LEAP-RE Kick-OFF MEETING 23-24 March 2021
Work Package WP4
Maximising Outcomes

## Slide 2: WP4: Introduction
WP4 implements tasks to support the LEAP-RE projects to achieve and maximise their intended outputs and outcomes, assuring mutual learning, support and service delivery, and strategic communication.
Objectives of this WP are:
Expand and manage a quadruple helix community and stakeholders
Collect input and feedback from this community
Leverage the results, knowledge, and activities of the projects to optimize outputs and outcomes
Facilitate and support the uptake of innovation, and future upscaling and replication
Coordinate public communications and awareness-raising
WP duration:
M3-M63
Partners involved:
Task Leaders: UH & AESG
Contributors: LGI; DSI; POLIMI; SU; MESRS; ANR; PAUWES; DLR

## Slide 3: WP4: Milestones and Outcomes
Main WP expected results:
  Animation and expansion of the LEAP-RE Community
  Development of a strategy for knowledge sharing and clustering
  Development of an appropriate knowledge management system
  Building and Managing an online repository and community social network
  Organizing Stakeholder surveys
  Development of an online training platform
  Publishing LEAP-RE state-of-the-art Reports
  Updating and/or review of existing MARs
  Scientific dissemination
  Organizing Winter/Summer schools
  Innovation acceleration
  Programme communication
WP Milestones:
  Workshop 1 (M21), UH
  Workshop 2 (M45), AESG
  Workshop 3 (M61), UH

## Slide 4: WP4: Task 4.1
Task 4.1:Expanding, managing and animating the LEAP-RE community
The aim of this task is to support the further development and management of a long-lasting, quadruple helix LEAP-RE community, comprising government agencies, academia, civil society organizations, and the private sector.
Leaders:UH; AESG
Contributors: LGI; DSI; POLIMI; SU; MESRS; ANR; PAUWES; DLR
Action 1: Organise LEAP-RE General Workshops
  Workshop 1
  Workshop 2
  Workshop 3
Action 2: Clustering Pillar 1 & 2 Projects
  Strategy for knowledge sharing and clustering
  Identify and form clusters of projects
  Three clustering sessions at General Workshops
Action 3: Animate online community
  Build and manage an online repository
  Continuous online animation
  Organise Stakeholder surveys
Deliverables:
D4.1 Knowledge sharing and clustering strategy (M5), UH
D4.2 Results from clustering in LEAP-RE (M60), UH
D4.3 Strategic approach to LEAP-RE Community management (M3), LGI
D4.4 Online repository of LEAP-RE Horizontal Training Modules (M12), LGI

## Slide 5: WP4: Task 4.2
Task 4.2.: Knowledge capitalisation, valorisation, & scientific dissemination
The aim of this task is to build on the work undertaken in Pillars 1 &2, WP4, and in WP5 in the field of M&E to create a programme-level valorisation effort for the knowledge and scientific results & outcomes coming from the LEAP-RE projects.
Task Leaders: POLIMI; SU
Contributors: UH; AESG; LGI; DSI; MESRS; ANR; PAUWES; DLR
Action 1: Publish LEAP-RE state-of-the-art reports M18-M63
  SOTA 1 – Linked to General Workshop 1
  SOTA 2 – Linked to General Workshop 2
  SOTA 3 – Linked to General Workshop 3
Action 2: Reflect on and update the MARs M51-M57
  Reviewing MARs
  Updating MARs
Action 3: Coordinate Scientific dissemination M6-M63
  Scientific dissemination guidelines
  Monitor & report dissemination activities
  Interface with scientific databases & networks
Action 4: Organize Winter/Summer Schools M19-M58
  Summer school
  Winter school
  Virtual PhD pitching contest
Deliverables:
D4.5 Proceedings from general workshops (M21, M45, M60), POLIMI
D4.6 Updated and Revised Multiannual Roadmaps (M54), POLIMI
D4.7 List of LEAP-RE Dissemination Activities (M18, M36, M60), POLIMI

## Slide 6: WP4: Task 4.3
Task 4.3.: Innovation Accelerator
The aim of this task is to support the further development of innovative solutions, products and services arising from the LEAP-RE R&I projects, by offering services and connecting the LEAP-RE community to relevant actors in the innovation support and financial sectors.
Task Leader: LGI
Contributor: PAUWES
Action 1: Acceleration Services
  Developing innovation accelerator services
  Providing innovation accelerator services
Action 2: Liaison with multiplier networks
  Connect local entrepreneurs to networks
Action 3: Manage Innovation Scaling Group
  Connect projects and innovators with actors network
Deliverables:
D4.8 Detailed description of the Innovation Accelerator (M24), LGI
D4.9 Analytical Report: Good Practices on Innovation Acceleration (M56), LGI

## Slide 7: WP4: Task 4.4
Task 4.4.: Programme communication
The aim of this task is to coordinate and implement the LEAP-RE programme’s communication activities, including the communication activities undertaken in Pillar 1 & 2 projects.
Task Leader: DSI
Contributors: AESG; LGI
Action 1: LEAP-RE Communication & Awareness Strategy
  LEAP-RE communication plan
  Guidelines for P1&2 project communications
  Ensure period reporting on communication activities
Action 2: Coordinating communication actions in P1&2 projects
  Project communication, including social media
  Coordination of communication activities
Action 3: LEAP-RE Communication materials
  Design and publish materials (print and web)
  Design and maintain website
  Design & maintain social media accounts
Deliverables:
D4.10 LEAP-RE Communication and Awareness Raising strategy (M2), DSI
D4.11 LEAP-RE Website (M3), LGI

## Slide 8: WP4: interactions with other WP
INPUT |  |  |  | OUTPUT
Contribute to planning & organizing, including scientific programme (WPs 2, 3) and stakeholder engagement and long-term perspective (WPs 5, 6) |  | LEAP-RE General Workshops |  | Opportunity for experience sharing, networking, and other interactions with Pillar 1 & 2 projects and stakeholders (WPs 2, 3, 5, 6)
Contribute to methodology, strategy, information sharing (WPs 2, 3, 5, 8) |  | Clustering Pillar 1 & 2 Projects |  | Clusters of projects (WPs 2, 3, 5)
Contribute to definition of surveys (WPs 5, 6) |  | Stakeholder Surveys |  | Results informing work (WPs 5, 6)
Contribute to data collection for updated SOTA (WPs 2, 3) |  | Publish LEAP-RE SOTA Reports |  | Results informing development of long-term perspective and reports on RE research capacity (WPs 5, 6)
Sharing experiences from coordinating and implementing pillars 1 & 2 projects, results from RE research capacity and stakeholder dialogue (WPs 2, 3, 5, 6) |  | Updating MARS |  | Results informing development of long-term perspective and reports on RE research capacity (WPs 5, 6)
Publication strategy developed in WP3, Mapping of R&I assets in pillar 2 projects in WP3, and RE research capacity (WPs 3, 5) |  | Coordinate scientific dissemination |  | Input to scientific dissemination guidelines and support to Pillar 1 & 2 projects (WP2, 3), support RE research capacity report (WP5)
Training and capacity building activities designed in WP3 |  | Winter / Summer schools |  | Supporting long-term strategy for capacity building (WP5)
Needs for acceleration services, links to funders (WPs 2, 3) |  | Acceleration services |  | Contribution to future funding calls and long-term agendas (WP8, 5, 6)
Information and input for programme communication (all WPs and pillar 1 & 2 projects) |  | Programme communication |  | Internal and external communication tools (all WPs and pillar 1 & 2 projects)

## Slide 9: WP4: Actions to be done

## Slide 10: WP4: Actions to be done

## Slide 11: WP4: Actions to be done

## Slide 12: WP4: Risk assessment
Risk Name | Impact if occurs | Preventive / Contingency action
Uncertainties linked to COVID pandemic | Low | Use of virtual meetings and other virtual options
Lack of alignment of some partners | Mid | Coordination with PMB, regular WP meetings, mid-term reports
Complexity impacting delivery | Mid | Detailed work plan, regular WP meetings, mid-term reports
Limited interaction with other WPs | Mid | Regular participation of WP leaders in PMB meetings, regular WP meetings, participation of non-funded partners to in linked tasks