## Slide 1
LEAP-RE Kick-OFF MEETING 23-24 March 2021
Work Package 5
Long-term Perspective

## Slide 2
Long-term Perspective
5

## Slide 3
Duration: M3 (Dec. 2020) – M63 (Dec. 2025)
Partners involved:
WP 5: Introduction

## Slide 4
Main WP objectives:
Developing the long-term perspective for the AU-EU partnership in RE STI
Monitoring, Evaluation & Learning (MEL) Concept
MEL process with Pillar 1, Pillar 2 and Pillar 3 activities
Dialogues with policymakers and other stakeholders for research uptake
A Strategies for RE research-capacity in Africa
Strategy guidelines and plan for the design of the long-term partnership
WP 5: Introduction

## Slide 5
Main WP expected results:
  Baseline study | Theoretical framework development | MEL Plan | Monitoring | Evaluation | Learning
  Analysis about R&I capacities in Africa
  Twinning & Teaming & Pooling activities
  List of new LEAP-RE community members
  Strategy guidelines and a plan for the design of the long-term partnership
Main WP milestones:
  M55: Launch of the future partnership in M58 (Jul. 2025)
WP 5: Milestones and outcomes

## Slide 6
Task 5.1: M&E Concept and Impact Assessment
Leaders and contributing partners: Ms Elena SIMION (UEFISCDI) | Ms Anne W. Wambugu & Ms Hope N Njoroge (SU) | Mr Stefan A. Haffner (DLR) | Mr Abdellatif Zerga & Mr Erick Tambo (PAUWES) | Mr Mokthar Sellami & Mr Belarbi Yacine & Ms Souami Feriel (MESRS) | Ms Elke Dall & Mr Dietmar Lampert & Mr Utku Demir (ZSI)
Duration: (M3 (Dec. 2020) - M63 (Dec. 2025))
Main Activities: Monitoring, Evaluation and Learning
Methodology : Baseline study | Theoretical framework development | MEL Plan | Monitoring | Evaluation | Learning
Expected results: MEL Plan and MEL Reports for all three Pillars of the project
Deliverables:
WP 5: Task 5.1
Year | Number | Title | Due Date | Responsible
2021 | D5.1 | Theory of Change, M&E Approach and MEL Plan | M9 ¦ Jun. 2021 | SU – Anne W. Wambugu
2025 | D5.2 | Report on Monitoring | M53 ¦ Feb. 2025 | SU - Anne W. Wambugu
 | D5.3 | Report on Evaluation and Learning | M61 ¦ Oct. 2025 | UEFISCDI - Elena SIMION

## Slide 7
Task 5.2: Dialogue with Policymakers and other Stakeholders for Research Uptake
Leaders and contributing partners: Mr Abdellatif Zerga & Mr Erick Tambo (PAUWES) | Mr Stefan A. Haffner (DLR) | Mr Mokthar Sellami & Mr Belarbi Yacine & Ms Souami Feriel (MESRS) | Ms Emanuela Colombo & Mr Riccardo Mereu (POLIMI) | Ms Niclette Bukasa Kampata (LGI)
Duration: (M3 (Dec. 2020) - M63 (Dec. 2025))
Main Activities: Institutional dialogues with policy makers and other stakeholders
Methodology: (Virtual) Round table discussions:
1) “Theory of Change and Impact Pathway in Multi-lateral Cooperations?”, 2) “Monitoring, Evaluation and Learning in an AU-EU Knowledge Management and Communication Framework”, 3) “Coordinated Communication in the Stakeholder’s Network Labyrinth”, 4) “AU-EU Knowledge Hubs System”
Expected results: Contributions to the ‘Strategy guidelines and plan for the design of the long-term partnership’
Deliverables:
WP 5: Task 5.2
Year | Number | Title | Due Date | Responsible
2024 | D5.5 | Research briefs based on Pillar 1 and Pillar 2 results for dialogue with external policy and stakeholder partner | M40 ¦ Jan. 2024 | PAUWES – Erick Tambo
 | D5.4 | Proceedings of round tables for research uptake | M43 ¦ Apr. 2024 | PAUWES – Erick Tambo

## Slide 8
Task 5.3: Strategy for RE research-capacity in Africa
Leaders and contributing partners: Mr Mokthar Sellami & Mr Belarbi Yacine & Ms Souami Feriel (MESRS) | Ms Elke Dall & Mr Dietmar Lampert & Mr Utku Demir (ZSI) | Ms Tinyiko Ntshongwana & Ms Refilwe Mashigo (DSI) | Ms Anne W. Wambugu& Ms Hope N Njoroge | Strathmore University (SU)
Duration: (M3 (Dec. 2020) - M63 (Dec. 2025))
Main activities: Analysis, mapping & visualization of networks, evaluation
Methodology / suggested approach: Benchmarking, bibliometric analysis, questionnaire prep.
Task expected results: Report on RE-related R&I capacities, excellence centres in Africa as well as research co-operation and institutional networks with other regions.
Deliverables:
WP 5: Task 5.3
Year | Number | Title | Due Date | Responsible
2021 | D5.8 | Report on the analysis about R&I capacities in Africa | M15 ¦ Dec. 2021 | MESRS – Mokthar Sellami
2025 | D5.9 | Report about Twinning & Teaming & Pooling activities | M58 ¦ Jul. 2025 | MESRS – Mokthar Sellami

## Slide 9
Task 5.4: Strategic ambition of the long-term partnership
Leaders and contributing partners: Mr Abdellatif Zerga & Mr Erick Tambo (PAUWES) | Mr Stefan A. Haffner (DLR) | Ms Elena SIMION (UEFISCDI) | Ms Anne W. Wambugu & Ms Hope N Njoroge (SU) | Ms Kibibi Ndope (AESG) | Ms Melissa Plath | HELSINGIN YLIOPISTO (HU)
Duration: (M3 (Dec. 2020) - M63 (Dec. 2025))
Main activities: Analysis, document writing, internal virtual workshop(s)
Methodology: Collating lessons learned from external actors.
Expected results: Strategy guidelines and a plan for the design of the long-term partnership & List of new LEAP-RE community members
Deliverables:
WP 5: Task 5.4
Year | Number | Title | Due Date | Responsible
2024 | D5.11 | Strategy design workshop for the future platform and documentation of lessons learned from external actors | M50 ¦ Nov. 2024 | DLR - Stefan A. Haffner
2025 | D5.6 | Funding opportunities to enhance additional activities | M53 ¦ Feb. 2025 | PAUWES – Erick Tambo
 | D5.7 | List of new LEAP-RE community members | M53 ¦ Feb. 2025 | DLR - Stefan A. Haffner
 | D5.10 | Strategy guidelines and plan for the design of the long-term partnership | M53 ¦ Feb. 2025 | DLR - Stefan A. Haffner

## Slide 10
Input:
T5.1: List inputs from other WPs necessary to execute this WP
T5.2: List inputs from other WPs necessary to execute this WP
T5.3: No initial input needed
T5.4: List inputs from other WPs necessary to execute this WP
Output:
T5.1: List outputs from this WPs necessary to execute the work in other WP
T5.2: List outputs from this WPs necessary to execute the work in other WP
T5.3: WP9, WP11, WP13, WP14 (by providing related bibliometric data), WP12, WP15 (by providing related results of the analysis).
T5.4: List outputs from this WPs necessary to execute the work in other WP
WP 5-interactions with other WP

## Slide 11
Add any actions already implemented (such as preparatory work) in the first months of LEAP-RE
T5.1: Describe any actions
T5.2: Describe any actions
T5.3: Keyword identification for the bibliometric analysis, query comparison to measure the validity of the expected input data.
T5.4: Describe any actions
WP 5: Actions done in the first months

## Slide 12
Actions list:
Add actions to launch/implement in the first 6 months
T5.1: describe actions / expected delivery date / responsible person
T5.2: describe actions / expected delivery date / responsible person
T5.3: (i) Bechmarking / M12 (ii) Bibliometric Research / M6 / ZSI-Team (Elke Dall, Dietmar Lampert, Utku Demir)
T5.4: describe actions / expected delivery date / responsible person
WP 5: Actions to be done

## Slide 13
Risk assessment and Contingency plan
Describe any risk associated to the implementation of the work to be carried out / add a contingency action / feel free to use a table
WP 5:Risk assessment
Risk Name | Impact if occurs | Preventive / Contingency action